## Tasks
Task ID | Task Name | Owner | Status | Priority | Start Date | Due Date | % Complete | Notes
TSK-001 | Requirements gathering | Alice | Complete | High | 2024-01-15 | 2024-02-01 | 100%
TSK-002 | System design | Bob | Complete | High | 2024-02-01 | 2024-03-01 | 100%
TSK-003 | Backend development | Charlie | In Progress | High | 2024-03-01 | 2024-05-01 | 65% | On track
TSK-004 | Frontend development | Diana | In Progress | Medium | 2024-03-15 | 2024-05-15 | 40%
TSK-005 | API integration | Eve | Not Started | Medium | 2024-04-01 | 2024-05-01 | 0% | Blocked by TSK-003
TSK-006 | Testing | Frank | Not Started | High | 2024-05-01 | 2024-06-01 | 0%
TSK-007 | Documentation | Grace | Not Started | Low | 2024-05-15 | 2024-06-15 | 0%
TSK-008 | Deployment | Alice | Not Started | Critical | 2024-06-01 | 2024-06-15 | 0%
Note on H4: Updated 2024-03-20
Note on E5: Blocked until backend API is ready